NEXORA TECHNOLOGIES PVT. LTD.

PROJECT AURORA
PROJECT CHARTER & DELIVERY DOCUMENTATION

| Field | Value |
| --- | --- |
| Document ID | NEX-PROJ-AUR-001 |
| Version | 1.0 |
| Status | Active — Delivery |
| Project Sponsor | Priya Menon, Chief Product Officer |
| Project Manager | Arjun Rao, Senior Program Manager |
| Business Owner | Customer Experience & Digital Products |
| Technical Lead | Neha Kulkarni |
| Target Launch | 15 December 2026 |
| Planned Duration | 01 July 2026 – 15 December 2026 |
| Classification | Internal |

# 1. Executive Summary

Project Aurora is a Nexora initiative to build a unified employee-facing customer-support workspace that brings customer conversations, case history, knowledge articles and workflow actions into one operational interface. The objective is to reduce support-agent context switching and improve first-contact resolution while maintaining appropriate access controls and auditability.

Aurora is planned as a phased delivery. Phase 1 focuses on the core workspace, case search, knowledge retrieval, customer timeline and role-based access. Later capabilities may include intelligent case summarization, recommended responses and workflow automation, subject to security and business approval.

# 2. Business Case

| Problem | Current Impact | Aurora Response |
| --- | --- | --- |
| Information spread across systems | Agents spend time switching between tools and searching manually | Unified workspace with contextual search |
| Repeated customer questions | Agents recreate answers from multiple knowledge sources | Central knowledge retrieval and article linking |
| Limited case context | Agents may lack prior interactions during handoffs | Customer timeline and related-case view |
| Inconsistent handling | Different agents may follow different procedures | Approved workflows and knowledge guidance |
| Manual reporting | Operational metrics require data consolidation | Standardized event and case telemetry |

The business case establishes the expected operational benefits and provides the baseline for measuring Aurora's effectiveness during the pilot.

# 3. Objectives and Success Criteria

Reduce average agent time spent locating relevant customer information by at least 30% during pilot measurement.

Increase first-contact resolution by 10% relative to the agreed pilot baseline.

Provide a single searchable workspace for approved case, customer and knowledge information.

Maintain role-based access so users see only information authorized for their role.

Achieve ≥99.5% availability during the production pilot window, excluding approved maintenance.

Complete security, privacy and operational readiness reviews before production launch.

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Information lookup time | -30% vs baseline | Timed pilot tasks |
| First-contact resolution | +10% vs baseline | Support analytics |
| Workspace availability | ≥99.5% | Platform monitoring |
| Critical security findings | 0 open at launch | Security review |
| Pilot adoption | ≥80% of assigned agents active weekly | Usage telemetry |

# 4. Scope

## 4.1 In Scope

Agent workspace with customer and case context.

Search across approved customer-support knowledge sources.

Customer interaction timeline and related-case visibility.

Role-based access control and audit logging.

Case notes, status updates and links to approved knowledge articles.

Operational dashboards for pilot adoption and key workflow metrics.

Integration with the Nexora Support Case API and Knowledge Repository.

## 4.2 Out of Scope

Replacing the existing customer master system.

Automated customer decisions involving refunds, credit or eligibility.

Unapproved external data sources.

Fully autonomous customer responses.

Migration of historical records outside the agreed pilot dataset.

Mobile-native application in the initial release.

# 5. Stakeholders and Responsibilities

| Role | Name / Group | Primary Responsibility |
| --- | --- | --- |
| Sponsor | Priya Menon | Funding, strategic decisions, executive escalation |
| Project Manager | Arjun Rao | Plan, dependencies, risks, status and delivery coordination |
| Technical Lead | Neha Kulkarni | Architecture, technical decisions and engineering quality |
| Product Manager | Rohan Shah | Requirements, prioritization and acceptance |
| UX Lead | Meera Iyer | Research, workflows and interface design |
| Security | Information Security Team | Threat review, controls and security sign-off |
| Data/Platform | Data Platform Team | Data pipelines, reliability and integration support |
| Business Users | Support Operations | Pilot feedback, UAT and adoption |

# 6. Delivery Plan and Milestones

| Milestone | Target Date | Deliverable | Exit Criteria |
| --- | --- | --- | --- |
| Charter & discovery | 15 Jul 2026 | Approved requirements and process map | Sponsor/product approval |
| Architecture baseline | 31 Jul 2026 | Architecture and integration design | Technical review complete |
| UX prototype | 14 Aug 2026 | Clickable agent workflow | Product + support feedback incorporated |
| MVP build | 30 Sep 2026 | Core workspace and search | Engineering acceptance tests pass |
| Integration & hardening | 31 Oct 2026 | Integrated pilot build | Critical defects resolved |
| UAT | 20 Nov 2026 | Business acceptance results | UAT sign-off |
| Security & operational readiness | 30 Nov 2026 | Security/readiness assessment | No blocking findings |
| Pilot launch | 15 Dec 2026 | Production pilot | Go-live checklist approved |

Dates are planned targets. Any material change to the launch date, scope or budget must be recorded in the project change log and approved by the designated owner.

# 7. Architecture and Technical Approach

Aurora uses a modular web application architecture. The user interface communicates with an application/API layer, which orchestrates approved support systems and the knowledge repository. Authentication is handled through Nexora's approved identity service. Authorization is enforced at the application and data-access layers.

| Component | Purpose |
| --- | --- |
| Aurora Web App | Agent-facing workspace and search experience |
| Aurora API | Business logic, orchestration and access enforcement |
| Identity Service | Authentication and MFA integration |
| Support Case API | Case details, status and interaction metadata |
| Knowledge Repository | Approved support articles and procedures |
| Audit Service | Security and administrative event logging |
| Analytics Store | Pilot usage and operational metrics |

Sensitive data must not be copied into logs or analytics events unless explicitly approved.

Integrations must use service identities with least-privilege permissions.

API failures should degrade gracefully and provide a clear status to the user rather than inventing unavailable information.

Knowledge responses should identify the underlying approved article or source where the user experience supports citations.

# 8. Requirements

| ID | Requirement | Priority | Acceptance Summary |
| --- | --- | --- | --- |
| AUR-F01 | Search approved support knowledge | Must | Relevant results returned with source metadata |
| AUR-F02 | Display customer/case context | Must | Authorized case information visible in workspace |
| AUR-F03 | Role-based access | Must | Unauthorized records are blocked |
| AUR-F04 | Audit important user/admin actions | Must | Events captured with timestamp and actor |
| AUR-F05 | Create/update case notes | Should | Authorized agent can save and view notes |
| AUR-F06 | Pilot analytics | Should | Adoption and workflow metrics available |
| AUR-F07 | Suggested knowledge | Could | Relevant approved articles surfaced contextually |
| AUR-F08 | AI-generated case summary | Could | Only after separate safety/security approval |

# 9. Risk Register

| Risk | Impact | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Incorrect access permissions expose customer data | High | Medium | Role matrix, automated tests, security review | Security / Tech Lead |
| Integration API instability | High | Medium | Timeouts, retries, monitoring and fallback states | Tech Lead |
| Knowledge content becomes outdated | Medium | Medium | Content ownership, review dates and source metadata | Product |
| Low agent adoption | Medium | Medium | Pilot champions, training and usability testing | Business Owner |
| Scope expansion delays launch | High | High | Change control and must/should/could prioritization | Project Manager |
| AI summary produces unsupported statements | High | Low/Med | Treat as optional; require source grounding and approval | Product / Security |

# 10. Communication and Governance

| Cadence | Audience | Purpose | Owner |
| --- | --- | --- | --- |
| Daily stand-up | Core delivery team | Blockers and immediate work | Project Manager |
| Weekly status | Sponsor + stakeholders | Progress, risks, decisions | Project Manager |
| Fortnightly demo | Product + business users | Validate increment and gather feedback | Product Manager |
| Risk review | PM + leads | Review top risks and mitigations | Project Manager |
| Steering decision | Sponsor + required leads | Resolve scope/budget/launch issues | Sponsor |

Project status uses Green / Amber / Red. Green means delivery is on plan; Amber indicates a material issue requiring attention but with a credible recovery path; Red indicates a major blocker or objective likely to be missed without executive intervention.

# 11. Change Control

Record the requested change, reason, requester and date in the change log.

Assess impact on scope, schedule, cost, architecture, security, privacy and operations.

Identify whether existing requirements or milestones must change.

Obtain approval from the appropriate product/project owner.

Update the baseline plan and communicate the decision to affected stakeholders.

| Change ID | Example | Approval |
| --- | --- | --- |
| CR-001 | Add an additional support-system integration | Product + Technical Lead |
| CR-002 | Move pilot launch by more than 2 weeks | Sponsor + Project Manager |
| CR-003 | Introduce a new category of sensitive customer data | Security + Business Owner |

# 12. Testing and Release Readiness

Unit and integration tests must cover critical business logic and access-control paths.

UAT must include normal, edge-case and unauthorized-access scenarios.

Security testing must cover authentication, authorization, session handling, logging and common web/API risks.

Production deployment requires a rollback plan, monitoring, support ownership and approved release notes.

Open critical defects or unresolved security blockers prevent launch.

Release readiness is a joint decision across Product, Engineering, Information Security and Operations; passing a technical test alone does not constitute business approval.

# 13. Pilot and Rollout Plan

Select a representative pilot group from Support Operations.

Train pilot users and provide a short quick-start guide.

Run controlled pilot tasks against an approved dataset.

Collect quantitative metrics and qualitative feedback.

Review incidents, defects, adoption and success criteria.

Approve, extend, revise or stop the pilot based on evidence.

The initial pilot is intended to validate workflow fit and operational value before broader deployment.

# 14. Current Status Snapshot

| Area | Status | Notes |
| --- | --- | --- |
| Scope | Green | MVP scope agreed |
| Architecture | Green | Baseline under technical review |
| UX | Green | Prototype feedback cycle active |
| Integrations | Amber | Dependency on Support Case API readiness |
| Security | Amber | Threat review scheduled before UAT exit |
| Timeline | Green | Launch target remains 15 Dec 2026 |
| Adoption | Not Started | Pilot group to be selected before UAT |

# 15. Key Decisions and Open Questions

## 15.1 Decisions

Aurora will not autonomously make customer eligibility, refund or credit decisions in the initial release.

Access will be role-based and auditable.

The initial release prioritizes approved internal sources over broad external web search.

AI-generated summaries, if included, must be grounded in approved source data and separately approved.

## 15.2 Open Questions

Which support teams will form the final pilot cohort?

What exact baseline period will be used for first-contact-resolution measurement?

Which additional support-system integration is highest priority after MVP?

Who owns review and retirement of Aurora knowledge articles?

What retention period applies to Aurora audit events and pilot analytics?

# 16. Project Documentation Index

| Artifact | Purpose | Owner | Status |
| --- | --- | --- | --- |
| Project Charter | Purpose, scope, objectives, governance | Project Manager | Approved |
| Requirements Register | Detailed functional/non-functional requirements | Product Manager | Active |
| Risk Register | Risks, impact, mitigation and ownership | Project Manager | Active |
| Decision Log | Material project decisions and rationale | Project Manager | Active |
| Change Log | Approved changes to baseline | Project Manager | Active |
| UAT Plan & Results | Business validation and acceptance | Business Owner | Planned |
| Release Checklist | Production readiness controls | Technical Lead | Planned |
| Closure & Lessons Learned | Outcome review and improvement actions | Project Manager | Planned |

# 17. Frequently Asked Questions

What is Project Aurora? Aurora is a unified support workspace intended to reduce agent context switching and improve access to approved customer and knowledge information.

When is Aurora planned to launch? The current target launch date is 15 December 2026, subject to readiness and approvals.

Who owns Aurora? The business owner is Customer Experience & Digital Products; the project is sponsored by the Chief Product Officer.

Is Aurora replacing the customer master system? No. Replacing the customer master system is explicitly out of scope.

Will Aurora automatically respond to customers? Not in the initial release. Fully autonomous customer responses are out of scope.

Can Aurora show any customer record to any employee? No. Role-based authorization is a mandatory requirement.

What should happen if an integration is unavailable? The application should show an explicit unavailable/degraded state rather than fabricate missing information.

# 18. Approval

| Approval Role | Name | Status |
| --- | --- | --- |
| Project Sponsor | Priya Menon | Approved |
| Project Manager | Arjun Rao | Approved |
| Business Owner | Customer Experience & Digital Products | Approved |
| Technical Lead | Neha Kulkarni | Approved |
| Information Security | Information Security Team | Required before production launch |